Project Two

Advance Embedded System Design

Embedded Vehicle System

Harsimran Singh Bindra
Yasir Aslam Shah

The following document presents the Project Plan
S. No	Task	Member	Date
1	Develop System Architecture	Harsimransingh & Yasir	April 10
2	Phase I- Free RTOS Ultra sonic Sensor Integration	Harsimransingh	April 15
3	Phase II - Beagle Bone Thread Creation (Logger, Decision, Heartbeat)	Yasir	April 12
4	Phase I- Free RTOS Accelerometer Sensor Integration	Harsimransingh	April 20
5	Phase II- Beagle Bone Thread inter - Communication	Yasir	April 15
6	Phase I- Free RTOS Multi sensor integration	Harsimransingh	April 22
7	Phase II- Beagle Bone UART Communication	Yasir	April 24
8	Phase I- Free RTOS UART Communication	Harsimransingh	April 24
9	Unit Testing	Harsimransingh & Yasir	April 25
10	Phase I and Phase II integration	Harsimransingh & Yasir	April 26
11	Test Conditions and Corner Cases	Harsimransingh & Yasir	April 27
12	Documentation Report	Harsimransingh & Yasir	April 28
13	Extra Credit (Buzzer etc)	Harsimransingh & Yasir	April 29